## TaskList-Done
Task List - Done
Team No. |  | 11 |  |  |  |  | Supervisor |  | Mr. Andrew Lam
Team Member |  | GREGORY KOH WEN CONG | Greg | 104 | 107 |  | From | 15.Feb.2016
|  | JACELA JOB ANDREW CLARK | Job | 52 | 84 |  | To | 4.Mar.2016
|  | ALMEDA GLENN PAOLO MAESTRO | Glenn | 73 | 84
|  | POH JUN WEI, RAYSON | Rayson | 79 | 95
No. | Title |  | Assign | Est. | Act. | Note / Comment / Issue
1 | Framework |  | Greg | 2 | 2
2 | Player |  | Greg | 5 | 5
3 | Jellybean System |  | Greg | 4 | 4
4 | Difficulty |  | Greg | 3 | 3
5 | Advanced Collision Detection(Bonding Box - AABB) |  | Greg | 5 | 5
6 | Probability |  | Greg | 2 | 2
7 | Load and Save Game |  | Greg | 6 | 6
8 | Change Font |  | Greg | 3 | 6 | Took longer than expected cause have calculate and input each character's width and stuff in the font generator
9 | Make Player class inherit from Object class |  | Greg | 5 | 5
10 | Tutorial Game 1 |  | Greg | 6 | 6
11 | Easy Game 1 |  | Greg | 5 | 5
12 | Medium Game 1 |  | Greg | 5 | 5
13 | Hard Game 1 |  | Greg | 5 | 5
14 | Difficulty Selection(At GameHub) |  | Greg | 5 | 6 | Take slightly longer than expected cause UI Animator and Animations got a slight problem. Glenn tried but failed.. :)
15 | Jellybean Selection(At GameHub) |  | Greg | 6 | 6
16 | Modify Level Select to Game Loader |  | Greg | 4 | 4
17 | Confirmation Popout Window |  | Greg | 4 | 4 | Confirmation Popout window for Game Loader and Game hub Scene
18 | Add Guardian and Exit at Game Hub |  | Greg | 9 | 9
19 | Add NPCs at Game Hub |  | Greg | 4 | 3 | Done one for now(Maybe more will be created later)
20 | Add AIs For Game1 |  | Greg | 3 | 3 | Only have one type of simple AI
21 | Instruction for Game 1's Tutorial |  | Greg | 3 | 3
22 | Start and Load Game Functionalities |  | Greg | 3 | 3
23 | Losing and Credits |  | Greg | 3 | 3
24 | Resolve Warnings |  | Greg | 4 | 4 | Managed to resolve most of the warnings except a few unknown ones
25 | Lua Scripts class |  | Job | 4 | 2 | May be developed more later
26 | Game Hub |  | Job | 8 | 10 | Completed with help from the others
27 | AI (FSM base class) |  | Job | 3 | 4
28 | AI (General base class) |  | Job | 2 | 8 | Just need to add some extra (good to have) AI styles
29 | Tutorial Game 2 |  | Job | 6 | 10 | Overlooked some features of my game; The tutorial level was a base for the other levels
30 | Easy Game 2 |  | Job | 5 | 10 | Actual hours includes time spent on optimisation
31 | Normal Game 2 |  | Job | 5 | 10
32 | Hard Game 2 |  | Job | 5 | 10
33 | Colours and door class |  | Job | 6 | 5 | Completed faster than expected
34 | GUI for game 2 |  | Job | 2 | 5 | Supervisor brought up interesting ways to make GUI better, so I followed his advice.
35 | Gantt Chart |  | Job | 2 | 4
36 | User Guide |  | Job | 2 | 3
37 | Work load (for submission) |  | Job | 2 | 3
38 | UI Feature |  | Rayson | 4 | 6 | Added more variables along the way to suit the needs of child classes
39 | UI Button |  | Rayson | 4 | 8 | A lot more troublesome trying to use this class to work with animation thus many trial and errors along the way.
40 | UI System |  | Rayson | 6 | 10 | Edited a whole lot of things to allow this class to compliment the other UIFeatures.
41 | UI Animation |  | Rayson | 10 | 16 | Spent a considerable amount of time and recoded after realising that the data structure was not optimal
42 | Tutorial Game 4 |  | Rayson | 10 | 18 | Actually redid the entire game with a entirely new concept and game logic thus the delay
43 | Easy Game 4 |  | Rayson | 7 | 4 | Having the skeleton structure of Tutorial Game 4's framework things were a lot easier to code
44 | Normal Game 4 |  | Rayson | 7 | 2 | A mere copy of easy Easy Game 4 with some change of variablesl Along with some debugging along the way
45 | Hard Game 4 |  | Rayson | 7 | 2 | A mere copy of easy Easy Game 4 with some change of variablesl Along with some debugging along the way
46 | MainMenu |  | Rayson | 4 | 4 | Added more variables along the way to suit the needs of child classes
47 | Settings |  | Rayson | 3 | 3 | Settings Icon To Navigate To Sound & Information
48 | Reset Button For Game 4 |  | Rayson | 3 | 3
49 | Solve Bug/Clear Warnings |  | Rayson | 2 | 3
50 | Tutorial Instructions For Game 4 |  | Rayson | 2 | 1 | Instruction Pop Up In Tutorial Game4
51 | Card Class |  | Rayson | 4 | 8 | Loads of Error Came Up When I Tried Integrating The Card Class Into My Game Scene
52 | Trigger Class |  | Rayson | 2 | 1 | Trigger Class To Use For Instructions
53 | Tutorial Phase |  | Rayson | 2 | 4 | Bugs Surfaced When I tried differentiating the levels when implementing the tutoprial phase.
54 | Information icon |  | Rayson | 2 | 2
55 | Sound System |  | Glenn | 8 | 6 | Integrated sound system with game state management, adjusted volume
56 | Game State and Scene Management |  | Glenn | 8 | 15 | Required optimization which took far longer than anticipated
57 | Tutorial Game 3 |  | Glenn | 3 | 3 | Finding the suitable questions turned out to be harder than it looks..
58 | Easy Game 3 |  | Glenn | 5 | 5 | Finding the suitable questions turned out to be harder than it looks..
59 | Medium Game 3 |  | Glenn | 5 | 5 | Finding the suitable questions turned out to be harder than it looks..
60 | Hard Game 3 |  | Glenn | 5 | 6 | Finding the suitable questions turned out to be harder than it looks..
61 | Base Object Class |  | Glenn | 8 | 4 | Turned out I missed out quite a few critical components..
62 | Fine tune Game 3 mechanics |  | Glenn | 3 | 6 | Optimization took far longer than expected
63 | Question and Answer class |  | Glenn | 2 | 3 | Was missing a few components initially.
64 | Pause Menu |  | Glenn | 4 | 5 | Was a little unfamiliar with UI engine initially
65 | GUI Improvement on Game 3 |  | Glenn | 2 | 2 | Able to improve GUI with help of Greg and Rayson
66 | Revise music volume |  | Glenn | 1 | 1 | Had the original files in computer so it's a quickly done
67 | Music on/off function |  | Glenn | 3 | 3 | Required a few adjustments to Game State Management
68 | Refine Pause Menu |  | Glenn | 3 | 2 | Just changing the colors
69 | Instruction for Game 3's Tutorial |  | Glenn | 3 | 3 | Show instructions when playing tutorial of Game 3
70 | Game report |  | Glenn | 6 | 6 | 20 page report up...
71 | Waypoints |  | Glenn | 2 | 3 | Waypoints set up for AI to move on, will need AI to work to test
72 | Presentation slides |  | Glenn | 5 | 3 | Ready to present
73 | Trailer video |  | Glenn | 4 | 3 | A 30 second trailer that features some items
74
75
76
Total |  |  |  | 298 | 355
Comment
(Any comment for this sprint?)
GREGORY KOH WEN CONG |  |  |  | JACELA JOB ANDREW CLARK
ALMEDA GLENN PAOLO MAESTRO |  |  |  | POH JUN WEI, RAYSON

## Task List - Week 1
Task List - Done (Week 1)
Team No. |  | 11 |  |  |  |  | Supervisor |  | Mr. Andrew Lam
Team Member |  | GREGORY KOH WEN CONG | Greg | 35 | 38 |  | From | 15.Feb.2016
|  | JACELA JOB ANDREW CLARK | Job | 22 | 34 |  | To | 4.Mar.2016
|  | ALMEDA GLENN PAOLO MAESTRO | Glenn | 40 | 34
|  | POH JUN WEI, RAYSON | Rayson | 24 | 32
No. | Title |  | Assign | Est. | Act. | Note / Comment / Issue
1 | Framework |  | Greg | 2 | 2
2 | Player |  | Greg | 5 | 5
3 | Jellybean System |  | Greg | 4 | 4
4 | Difficulty |  | Greg | 3 | 3
5 | Advanced Collision Detection(Bonding Box - AABB) |  | Greg | 5 | 5
6 | Probability |  | Greg | 2 | 2
7 | Load and Save Game |  | Greg | 6 | 6
8 | Change Font |  | Greg | 3 | 6 | Took longer than expected cause have calculate and input each character's width and stuff in the font generator
9 | Make Player class inherit from Object class |  | Greg | 5 | 5
10 | Lua Scripts class |  | Job | 4 | 2 | May be developed more later
11 | Game Hub |  | Job | 8 | 10 | Completed with help from the others
12 | AI (FSM base class) |  | Job | 3 | 4
13 | AI (General base class) |  | Job | 2 | 8 | Just need to add some extra (good to have) AI styles
14 | Easy Game 2 |  | Job | 5 | 10 | Overlooked game logic (harder than expected). Actual hours icludes time spent on optimisation.
15 | UI Feature |  | Rayson | 4 | 6 | Added more variables along the way to suit the needs of child classes
16 | UI Button |  | Rayson | 4 | 8 | A lot more troublesome trying to use this class to work with animation thus many trial and errors along the way.
17 | UI System |  | Rayson | 6 | 10 | Edited a whole lot of things to allow this class to compliment the other UIFeatures.
18 | UI Animation |  | Rayson | 10 | 16 | Spent a considerable amount of time and recoded after realising that the data structure was not optimal
19 | Sound System |  | Glenn | 8 | 6 | Integrated sound system with game state management, adjusted volume
20 | Game State and Scene Management |  | Glenn | 8 | 15 | Required optimization which took far longer than anticipated
21 | Tutorial Game 3 |  | Glenn | 3 | 3 | Finding the suitable questions turned out to be harder than it looks..
22 | Base Object Class |  | Glenn | 8 | 4 | Turned out I missed out quite a few critical components..
23 | Question and Answer class |  | Glenn | 2 | 3 | Was missing a few components initially.
24 | Waypoints |  | Glenn | 2 | 3 | Waypoints set up for AI to move on, will need AI to work to test
25
26
27
28
29
30
Total |  |  |  | 112 | 146
Comment
(Any comment for this sprint?)
GREGORY KOH WEN CONG |  |  |  | JACELA JOB ANDREW CLARK
ALMEDA GLENN PAOLO MAESTRO |  |  |  | POH JUN WEI, RAYSON

## Task List - Week 2
Task List - Done (Week 2)
Team No. |  | 11 |  |  |  |  | Supervisor |  | Mr. Andrew Lam
Team Member |  | GREGORY KOH WEN CONG | Greg | 40 | 41 |  | From | 15.Feb.2016
|  | JACELA JOB ANDREW CLARK | Job | 22 | 35 |  | To | 4.Mar.2016
|  | ALMEDA GLENN PAOLO MAESTRO | Glenn | 20 | 21
|  | POH JUN WEI, RAYSON | Rayson | 37 | 35
No. | Title |  | Assign | Est. | Act. | Note / Comment / Issue
1 | Tutorial Game 1 |  | Greg | 6 | 6
2 | Easy Game 1 |  | Greg | 5 | 5
3 | Medium Game 1 |  | Greg | 5 | 5
4 | Hard Game 1 |  | Greg | 5 | 5
5 | Difficulty Selection(At GameHub) |  | Greg | 5 | 6 | Take slightly longer than expected cause UI Animator and Animations got a slight problem. Glenn tried but failed.. :)
6 | Jellybean Selection(At GameHub) |  | Greg | 6 | 6
7 | Modify Level Select to Game Loader |  | Greg | 4 | 4
8 | Confirmation Popout Window |  | Greg | 4 | 4 | Confirmation Popout window for Game Loader and Game hub Scene
9 | Tutorial Game 2 |  | Job | 6 | 10 | Overlooked some features of my game; The tutorial level was a base for the other levels
10 | Normal Game 2 |  | Job | 5 | 10
11 | Hard Game 2 |  | Job | 5 | 10
12 | Colours and door class |  | Job | 6 | 5 | Completed faster than expected
13 | Tutorial Game 4 |  | Rayson | 10 | 18 | Actually redid the entire game with a entirely new concept and game logic thus the delay
14 | Easy Game 4 |  | Rayson | 7 | 4 | Having the skeleton structure of Tutorial Game 4's framework things were a lot easier to code
15 | Normal Game 4 |  | Rayson | 7 | 2 | A mere copy of easy Easy Game 4 with some change of variablesl Along with some debugging along the way
16 | Hard Game 4 |  | Rayson | 7 | 2 | A mere copy of easy Easy Game 4 with some change of variablesl Along with some debugging along the way
17 | Card Class |  | Rayson | 4 | 8 | Loads of Error Came Up When I Tried Integrating The Card Class Into My Game Scene
18 | Trigger Class |  | Rayson | 2 | 1 | Trigger Class To Use For Instructions
19 | Easy Game 3 |  | Glenn | 5 | 5 | Finding the suitable questions turned out to be harder than it looks..
20 | Medium Game 3 |  | Glenn | 5 | 5 | Finding the suitable questions turned out to be harder than it looks..
21 | Hard Game 3 |  | Glenn | 5 | 6 | Finding the suitable questions turned out to be harder than it looks..
22 | Pause Menu |  | Glenn | 4 | 5 | Was a little unfamiliar with UI engine initially
23
24
25
26
27
28
29
30
31
Total |  |  |  | 118 | 132
Comment
(Any comment for this sprint?)
GREGORY KOH WEN CONG |  |  |  | JACELA JOB ANDREW CLARK
ALMEDA GLENN PAOLO MAESTRO |  |  |  | POH JUN WEI, RAYSON

## Task List - Week 3
Task List - Done (Week 3)
Team No. |  | 11 |  |  |  |  | Supervisor |  | Mr. Andrew Lam
Team Member |  | GREGORY KOH WEN CONG | Greg | 29 | 28 |  | From | 15.Feb.2016
|  | JACELA JOB ANDREW CLARK | Job | 12 | 27 |  | To | 4.Mar.2016
|  | ALMEDA GLENN PAOLO MAESTRO | Glenn | 20 | 29
|  | POH JUN WEI, RAYSON | Rayson | 18 | 22
No. | Title |  | Assign | Est. | Act. | Note / Comment / Issue
1 | Add Guardian and Exit at Game Hub |  | Greg | 9 | 9
2 | Add NPCs at Game Hub |  | Greg | 4 | 3 | Done one for now(Maybe more will be created later)
3 | Add AIs For Game1 |  | Greg | 3 | 3 | Only have one type of simple AI
4 | Instruction for Game 1's Tutorial |  | Greg | 3 | 3
5 | Start and Load Game Functionalities |  | Greg | 3 | 3
6 | Losing and Credits |  | Greg | 3 | 3
7 | Resolve Warnings |  | Greg | 4 | 4 | Managed to resolve most of the warnings except a few unknown ones
8 | GUI for game 2 |  | Job | 2 | 8 | Supervisor brought up interesting ways to make GUI better, so I followed his advice.
9 | Gantt Chart |  | Job | 2 | 4
10 | User Guide |  | Job | 2 | 3
11 | Work load (for submission) |  | Job | 2 | 3
12 | Win/Lose triggers |  | Job | 4 | 9 | Needed a lot of help because I didnt expect it to be so difficult
13 | MainMenu |  | Rayson | 4 | 4 | Added more variables along the way to suit the needs of child classes
14 | Settings |  | Rayson | 3 | 3 | Settings Icon To Navigate To Sound & Information
15 | Reset Button For Game 4 |  | Rayson | 3 | 3
16 | Solve Bug/Clear Warnings |  | Rayson | 2 | 3
17 | Tutorial Instructions For Game 4 |  | Rayson | 2 | 3 | Instruction Pop Up In Tutorial Game4
18 | Tutorial Phase |  | Rayson | 2 | 4 | Bugs Surfaced When I tried differentiating the levels when implementing the tutoprial phase.
19 | Information icon |  | Rayson | 2 | 2
20 | Fine tune Game 3 mechanics |  | Glenn | 3 | 6 | Optimization took far longer than expected
21 | GUI Improvement on Game 3 |  | Glenn | 2 | 2 | Able to improve GUI with help of Greg and Rayson
22 | Revise music volume |  | Glenn | 1 | 1 | Had the original files in computer so it's a quickly done
23 | Music on/off function |  | Glenn | 3 | 3 | Required a few adjustments to Game State Management
24 | Refine Pause Menu |  | Glenn | 3 | 2 | Just changing the colors
25 | Instruction for Game 3's Tutorial |  | Glenn | 3 | 3 | Show instructions when playing tutorial of Game 3
26 | Game report |  | Glenn | 6 | 6 | 20 page report up...
27 | Presentation slides |  | Glenn | 5 | 3 | Ready to present
28 | Trailer video |  | Glenn | 4 | 3 | A 30 second trailer that features some items
29
30
31
32
33
Total |  |  |  | 89 | 106
Comment
(Any comment for this sprint?)
GREGORY KOH WEN CONG |  |  |  | JACELA JOB ANDREW CLARK
ALMEDA GLENN PAOLO MAESTRO |  |  |  | POH JUN WEI, RAYSON