## Week 1
Full Gantt chart for SP4
Week 1
*Updates section refers to constantly changing items (like debugging, minor edits) that aren't major tasks.
Task | Member assigned | Day of the week
|  | Mon | Tue | Wed | Thur | Fri | Weekends
Main Tasks: | Gregory
Framework
Player animations
Jellybeans system
Difficulty class
Bounding Box
Probability system
Load/Save game
Tutorial level
Updates:
Lua Scripts minor edits
Enhanced player class
Game 1 updates
Main Tasks: | Job
Lua Scripting Class
Set-up base tilemaps (aka csv files)
Door class
Game Hub
FSM (AI) base class
Updates:
Debugging game hub
Main Tasks: | Glenn
Music/Sounds system
Waypoints
Object class
Menu flow
Tutorial Games Base
Soundtrack
Base Game Scene
Tutorial Game 3
Updates:
Memory leak fixes
Debug object class
Tutorial game 3 updates
Main Tasks: | Rayson
UI System
Pathfinding AI class
UI Animator Class
UI Image class

## Week 2
Week 2
*Updates section refers to constantly changing items (like debugging, minor edits) that aren't major tasks.
Task | Member assigned | Day of the week
|  | Mon | Tue | Wed | Thur | Fri | Weekends
Main Tasks: | Gregory
Tutorial Game 1
Easy mode Game 1
Medium mode Game 1
Hard mode Game 1
Jellybean selection at game hub
Level unlocking system
Loading of saved game files
Confirmation box/Popup
Autosave
Updates:
Difficulty selection updates
Difficulty selection debugging
Main Tasks: | Job
Tutorial Game 2
Colour class
AI Base class
Easy mode Game 2
Medium mode Game 2
Hard mode Game 2
AI implementation
Updates:
Debugging Game 2 and AI class
Main Tasks: | Glenn
Tutorial Game 3
Question class
Answer class
Easy mode Game 3
Medium mode Game 3
Pause state
Hard mode Game 3
Updates:
Updates on object class
Debugging game 3
Main Tasks: | Rayson
Tutorial Game 4
Easy mode Game 4
Medium mode Game 4
Hard mode Game 4
Deck Class
Main menu UI
Updates:
UI system updates
Added more components into game 4
Debugging game 4

## Week 3
Week 3
*Updates section refers to constantly changing items (like debugging, minor edits) that aren't major tasks.
Task | Member assigned | Day of the week
|  | Mon | Tue | Wed | Thur
Main Tasks: | Gregory
AI Idling class
Game Hub state changes
Hub Guardian
Exit door @ hub
Autosave/Npc
Instructions for game 1
Lock and delete data
Jellybeans stats at end of levels
Reducing warnings for entire solution
Main Tasks: | Job
Updated AI class
Updated Game 2
Win/Lose triggers and screens
GUI improvements on game 2
Instructions for game 2
Documentation (gantt chart, user guide)
Main Tasks: | Glenn
Updated Game 3
Pause menu
Music on/off toggle and icon for main menu
GUI improvements for game 3
Instructions for game 3
Reduction of warnings for game 3
Documentation (Game report, trailer, ppt)
Main Tasks: | Rayson
Main Menu UI
Main menu settings
Instructions for game 4
Reduction of warnings for entire solution